## Cover page
| Nitrous Oxide Toolkit | Tab name | Cover Page | Description of tab | An introduction to the key actions checklist and how to use it
| UCLPartners | Date last updated | 2024-02-10
Date last updated | 2024-02-10
Key action checklist
This resource can be used independently or together with the Nitrous Oxide Waste Reduction Toolkit
What: the action list contains a list of comprehensive actions for any stage of the project work to reduce nitrous oxide waste, details on what to do and who can do it. It is not compulsory to use or follow this, but some teams may find it useful.
Who: this resource is intended for project managers. It is also useful for pharmacy, anaesthetics, estates and facilities colleagues working on nitrous oxide waste reduction initiatives.
When: it is best used from the start but can be picked up at any point in a project to reduce nitrous oxide gas waste.
How to use it:
The action list follows the recommended actions listed in the Nitrous Oxide Waste Reduction Toolkit.
Use the slicers to filter the actions by the stage a project is at. You can also then filter down further within this section if required, using the slicer in step two. The third slicer enables teams to filter actions by role.
Step one:
1. Click on the stage of project work, let's say you are at the start. |  |  | 2. Clicking on "Get started" in the first slicer will filter out actions not needed at this stage. |  |  |  | 3. All the actions at this stage will be shown in the table below the slicers, along with the suggested responsible role for each action.
Step two
Some stages reqire more steps than others. These stages can be filtered down further to see the different actions for each part.
1. Let's say you are ready to ensure the supply system is aligned to clinical use and you want to assess supply and clinical use |  |  | 2. You can see there are six parts to this stage |  |  | 3. You can further refine the actions by selecting one of these. If you do not select any, all actions will be listed. Let's say you want to assess supply and clinical use. |  | 4. The actions for assessing the supply and clinical use will be shown in the table below the slicers.
Step three
For any actions at any stage, you can use the third filter to see who is the recommended to complete the action. | [5 empty] | 2. All the actions for the project manager will be listed in the table below the slicers.
1. Let's filter by all the actions it is recommended that a project manager take on:
Other
To clear any filters select the icon on the top right of each slicer
To select multiple slicer options, on any slicker hold the CTRL key and select multiple filters

## Project stakeholder map (hidden)
Role | Name | Email | Contacted?
Project manager
Estates
Facilities
Porters
Anaesthetics
Endoscopy
ED
Maternity
Dentistry
Medical physics
Sustainability lead
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be per dept. may be able to identify no clinical uise straight away or to email / survey dept

## Simple decision path (hidden)
Site | Clinical destination of pipeline supply | Key contact | Manifold ID | Type | Does the department require any kind of nitrous oxide supply? | Decision | Column1
Site 1 |  |  | Manifold A | Nitrous oxide |  | Active | If F = no then Decsision = decomission
Site 2 |  |  | Manifold B | Pre-mixed 50% nitrous oxide and 50% oxygen |  | Active
Site 3 |  |  | Manifold C | Nitrous oxide |  | Active
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be per dept. may be able to identify no clinical uise straight away or to email / survey dept

## Detailed decision path (hidden)
Site | Clinical destination of pipeline supply | Key contact | Manifold ID | Type | Number of cylinders on the manifold | Size of cylinders | Contacted department? Y/N | Decision from department | Send survey to department? Y/N | If Y, comment on survey results: | Does procurement match clinical use? (Y/N) | Average N2O/O2 per birth | Is piped supply approproate?2 | Decision
Site 1 |  |  | Manifold A | Nitrous oxide |  | G-size | [6 empty] | Active | Active
Site 2 |  |  | Manifold B | Pre-mixed 50% nitrous oxide and 50% oxygen |  | G-size | [6 empty] | Active | Active
Site 3 |  |  | Manifold C | Nitrous oxide |  | G-size | [6 empty] | Active | Active
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be per dept. may be able to identify no clinical uise straight away or to email / survey dept

## Weighing for waste (hidden)
Site | Manifold ID | Type | Clinical destination of pipeline supply | Volume of gas purchased month 1 | Volume of gas purchased month 2 | Volume of gas purchased month 3 | Average volume of gas
Site 1 | Manifold A | Nitrous oxide |  | 6 | 6 | 6 | 52.56
Site 2 | Manifold B | Nitrous oxide |  | 10 | 35 | 66 | 324.12
Site 3 | Manifold C | Nitrous oxide |  | 23 | 5666 | 56 | 16775.4
Site 4 | Manifold D | Nitrous oxide |  | 4 | 55 | 5 | 186.88
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be per dept. may be able to identify no clinical uise straight away or to email / survey dept
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be per dept. may be able to identify no clinical uise straight away or to email / survey dept

## Maternity waste (hidden)
Site | Manifold ID | Clinical destination of pipeline supply | Volume of gas purchased month 1 | Volume of gas purchased month 2 | Volume of gas purchased month 3 | Average volume of gas purchased | Number of births month 1 | Number of births month 2 | Number of births month 3 | Average number of births | Average Usage Per Birth
Site 1 | Manifold A |  | 12 | 32 | 33 | 25.6667 | 22 | 333 | 22 | 125.6667 | 4.8961
Site 2 | Manifold B |  |  |  |  | #DIV/0! |  |  |  | #DIV/0! | #DIV/0!
Site 3 | Manifold C |  |  |  |  | #DIV/0! |  |  |  | #DIV/0! | #DIV/0!
Site 4 | Manifold D |  |  |  |  | #DIV/0! |  |  |  | #DIV/0! | #DIV/0!
`
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be per dept. may be able to identify no clinical uise straight away or to email / survey dept

## Equipment (hidden)
Supply option | Equipment | Supplier | Cost (Approximate) | Link
| Cylinders | BOC Healthcare, Air Liquide | Varies based on size and quantity | BOC Healthcare, Air Liquide
| Trolleys |  | £100-£300 per trolley
(or your chosen standalone supply option)
| Pressure regulators | BOC, RA Medical, Air Liquide | £50-£150 | BOC, RA Medical, Air Liquide
Yoke (for theatres only when retrofitting anaesthetic machines)
| Terminal unit caps | BOC | £30 per pack of 50 | BOC Shop
Schrader socket adaptors
Gas supply hose

## Key actions checklist
| Nitrous Oxide Toolkit | Tab name | Key Actions Checklist | Description of tab | This tab contains a list of comprehensive actions for any stage of the project work to reduce nitrous oxide waste, details on what to do and who can do it. It also provides links to other parts of the toolkit that can support these actions.
| UCLPartners | Date last updated | 2024-10-02 | Back to Introduction
Links to all supporting tools and guidance:
ID | Stage | Step | Actions | Suggested responsible role(s) | Owner | Due date | Notes | Status | Supporting tool or guidance | Supporting tool or guidance
1 | 1. Get started | A. Establish governance and assemble a project team | Identify and contact an executive sponsor for the project, such as the trust's net zero lead | Project manager |  |  |  | Not yet started | 3. Project management templates | 1. Nitrous oxide and nitrous oxide/oxygen mixture use and supply in the NHS
2 | 1. Get started | A. Establish governance and assemble a project team | Agree a governance structure including executive leadership, medical gas committee and a project lead | Project manager |  |  |  | Not yet started | 3. Project management templates | 2. Portable cylinder system options and equipment
3 | 1. Get started | A. Establish governance and assemble a project team | Contact and introduce the project to the medical gas committee using the toolkit and appropriate supporting resources | Project manager |  |  |  | Not yet started | 5. Project communication template | 3. Project management templates
4 | 1. Get started | A. Establish governance and assemble a project team | Add nitrous oxide waste mitigation and management as a regular item on the medical gas committee agenda | Medical gas committee |  |  |  | Not yet started |  | 4. Key actions checklist
5 | 1. Get started | A. Establish governance and assemble a project team | Gather your trust's data on nitrous oxide management, consumption and emissions from a) the Greener NHS dashboard and/or b) procurement data on nitrous oxide supply and usage in your hospital, and/or c) arrange site visits to manifold rooms to understand how gas is supplied in the medical gas pipeline system | Medical gas committee |  |  |  | Not yet started | 6. Approaches to understanding supply and use | 5. Project communication template
6 | 1. Get started | A. Establish governance and assemble a project team | Set up and populate the project management templates tool to track project progress | Project manager |  |  |  | Not yet started | 3. Project management templates | 6. Approaches to understanding supply and use
7 | 1. Get started | A. Establish governance and assemble a project team | Establish a multidisciplinary project team, define roles and responsibilities, and provide ongoing support - ensure the team includes healthcare professionals and clinical staff in the areas where the gas is used | Medical gas committee |  |  |  | Not yet started | 3. Project management templates | 7. Measure and calculate emissions and waste tool
8 | 1. Get started | A. Establish governance and assemble a project team | Set up team structure, documentation and governance to align members to the overall objectives of the work, role and responsibilities, communication methods and meetings | Medical gas committee |  |  |  | Not yet started |  | 8. Supply system map and decision template
9 | 1. Get started | A. Establish governance and assemble a project team | Draft a project one-pager that provides a project on a page (this can be updated and added to over time) | Medical gas committee |  |  |  | Not yet started | 5. Project communication templates | 9. Developing a business case
10 | 1. Get started | A. Establish governance and assemble a project team | Using data from action 5, assess the current state of nitrous oxide use and nitrous oxide waste reduction projects and identify where may be best to focus efforts first (gas type/location/hospital site) | Medical gas committee |  |  |  | Not yet started
11 | 1. Get started | A. Establish governance and assemble a project team | Schedule an initial kick-off meeting with all identified stakeholders to introduce the project and its goals | Project manager |  |  |  | Not yet started |  | Link to the main toolkit
12 | 1. Get started | A. Establish governance and assemble a project team | Agree regular opportunities to report progress to the medical gas committee | Medical gas committee |  |  |  | Not yet started
13 | 1. Get started | A. Establish governance and assemble a project team | Set realistic timelines for projects in collaboration with the project teams, taking into account factors such as staff availability and equipment procurement | Medical gas committee |  |  |  | Not yet started
14 | 1. Get started | A. Establish governance and assemble a project team | Establish a process for escalating issues or risks to executive leadership when needed | Medical gas committee |  |  |  | Not yet started
15 | 1. Get started | A. Establish governance and assemble a project team | Ensure safe medical gas supply continues and protocols comply with Health Technical Memorandum (HTM) | Medical gas committee |  |  |  | Not yet started
16 | 1. Get Started | A. Establish governance and assemble a project team | Store any documents, resources, data and insights in a secure manner, accessible to the team | Project manager |  |  |  | Not yet started
17 | 1. Get Started | A. Establish governance and assemble a project team | Regularly review and update project documents | Project manager |  |  |  | Not yet started | 3. Project management templates
18 | 1. Get Started | B. Engage key stakeholders | Identify and list all relevant stakeholders across different disciplines using the project management templates tool | Project manager |  |  |  | Not yet started | 3. Project management templates
19 | 1. Get Started | B. Engage key stakeholders | Create a stakeholder engagement plan | Project manager |  |  |  | Not yet started | 3. Project management templates
20 | 1. Get Started | B. Engage key stakeholders | Develop key messages about the purpose of the work | Project manager |  |  |  | Not yet started | 5. Project communication templates
21 | 1. Get Started | B. Engage key stakeholders | Identify risks and put in place strategies to mitigate them - start with the common challenges and appoaches identified in the 'Engage key stakeholders' part of the toolkit | Project manager |  |  |  | Not yet started | 3. Project management templates
22 | 1. Get Started | B. Engage key stakeholders | Implement engagement strategies such as schedule proactive meetings or surveys with key stakeholders (e.g anaesthetists, estates, pharmacists) | Project manager |  |  |  | Not yet started
23 | 1. Get Started | B. Engage key stakeholders | For multi-site projects, consider setting up specific working groups or stakeholder meetings for each hospital or department | Project manager |  |  |  | Not yet started
24 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Identify areas supplied with nitrous oxide and nitrous oxide/oxygen via medical gas pipeline systems and which manifold they are supplied from -you may request this information / a system map from the Medical Gas Committee or Estates and Facilities teams | Multidsciplinary project team |  |  |  | Not yet started | 8. Supply system map and decision template
25 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Source procurement data from the pharmacy procurement team | Project manager |  |  |  | Not yet started
26 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | For each area the piped supply provides gas to, identify contacts for the department or the clinical lead | Project manager |  |  |  | Not yet started | 3. Project management templates
27 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Agree dates, times and locations to visit manifolds and cylinder storage areas that supply nitrous oxide and/or nitrous oxide/oxygen mixture | Project manager |  |  |  | Not yet started | 8. Supply system map and decision template
28 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Agree dates, times and locations to visit clinical areas that use nitrous oxide and nitrous oxide/oxygen mixture to understand how gas is supplied and used Document the number and location of outlets using the Supply system map and decision template tool | Project manager |  |  |  | Not yet started | 8. Supply system map and decision template
29 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Assess how much nitrous oxide is being used clinically and clinicians' perceptions about potential changes, such as changing to a portable cylinder system -classify the clinical use of area (no/low/high) for each area using table 3 and decide what actions to take based on recommended decisions in table 3 using the Supply system map and decision template tool | Multidsciplinary project team |  |  |  | Not yet started | 8. Supply system map and decision template
30 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Analyse the procurement and clinial use data -compare how much nitrous oxide is being bought to how much is being used clinically to find any waste | Multidsciplinary project team |  |  |  | Not yet started | 7. Measure and calculate emissions and waste tool
31 | 2. Ensure supply of gas is aligned to clinical use | C. Assess supply and clinical use | Use the supporting resources to help establish what decision should be made for gas supply for each clinical area | Multidsciplinary project team |  |  |  | Not yet started | 8. Supply system map and decision template
32 | 2. Ensure supply of gas is aligned to clinical use | D. Plan supply system improvements | Plan the approach to supply system improvements (incremental or all at once) -consider the number of hospitals, PFI contracts, variability in engagement, infrastructure, budget availability and capacity of staff | Multidsciplinary project team |  |  |  | Not yet started
33 | 2. Ensure supply of gas is aligned to clinical use | D. Plan supply system improvements | As required, write a business case to enable decision making and funding for ensuring nitrous oxide or nitrous oxide/oxygen aligns to clinical need | Multidsciplinary project team |  |  |  | Not yet started | 9. Developing a business case
34 | 2. Ensure supply of gas is aligned to clinical use | E. Implement supply system alignment: No clinical use | Agree decomissioning of medical gas pipeline system and ensure sign off from relevant staff -confirm in writing to clinical leads, the Medical Gas Committee and estates/facilities colleagues | Project manager |  |  |  | Not yet started | 5. Project communication templates
35 | 2. Ensure supply of gas is aligned to clinical use | E. Implement supply system alignment: No clinical use | Securely cap all terminal units in the clinical area to prevent accidental use of the old piped system | Multidsciplinary project team |  |  |  | Not yet started
36 | 2. Ensure supply of gas is aligned to clinical use | E. Implement supply system alignment: No clinical use | Decommission the relevant medical gas pipeline: decommission the entire piped system if appropriate for all other clinical areas supplied by that manifold, or the specific branch that connects to the clinical area -select actions in the 'decomission' steps | Medical gas committee |  |  |  | Not yet started
37 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Decide if an initial pilot approach is useful to test the feasibility, effectiveness, and impact of transitioning to a portable cylinder system in one area, before rolling out more widely | Medical gas committee |  |  |  | Not yet started
38 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Agree transition from medical gas pipeline system to portable cylinder system and ensure sign off from relevant staff -use suppoting resources to confirm in writing to clinical leads, the Medical Gas Committee and estates/facilities colleagues | Project manager |  |  |  | Not yet started | 5. Project communication templates
39 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Agree pilot location (within theatres) and ensure sign off from relevant staff | Medical gas committee |  |  |  | Not yet started
40 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Contact the relevant stakeholders via meeting or email to set your objectives -plan regular updates to make sure everyone stays involved and the project moves forward, use the Internal messaging pack for help communicating the change | Project manager |  |  |  | Not yet started
41 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Make sure small cylinders are on the pharmacy's stock list and if not, request that your supplier representative adds them to the stock list | Multidsciplinary project team |  |  |  | Not yet started
42 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Check if the machines in the area can already use small cylinders - if so, you will not need to buy trolleys or decide an another approach to small cylinder supply | Multidsciplinary project team |  |  |  | Not yet started | 2. Portable cylinder system options and equipment
43 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Decide how many small cylinders you will need | Multidsciplinary project team |  |  |  | Not yet started | 6. Approaches to understanding supply and use
44 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Count how many outlets there are in the area, decide how many plugs to buy to make sure the outlets can be blocked off from use | Multidsciplinary project team |  |  |  | Not yet started
45 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Decide how much equipment you will need (if anaesthetic gas machines cannot use small cylinders) | Multidsciplinary project team |  |  |  | Not yet started | 2. Portable cylinder system options and equipment
46 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Choose a secure and accessible storage area for cylinders and equipment | Multidsciplinary project team |  |  |  | Not yet started
47 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Order equipment including cylinders, trolleys, plugs for wall valves, and anything else needed | Multidsciplinary project team |  |  |  | Not yet started
48 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Make sure the cylinders are stored safely when they arrive | Portering staff |  |  |  | Not yet started
49 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Train staff how to use the portable cylinders, including safety and troubleshooting -include training on using as much of the cylinder as possible before switching to a new cylinder | Multidsciplinary project team |  |  |  | Not yet started
50 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Let stakeholders know when the switch will happen using the template email in the supporting resources | Project manager |  |  |  | Not yet started | 5. Project communication templates
51 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: When cylinders arrive, have technicians set up the machines to use the small cylinders (only if anaesthetic gas machines can take these) | Multidsciplinary project team |  |  |  | Not yet started
52 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Securely cap all terminal units in areas switching to a portable cylinder supply system to prevent accidental use of the medical gas pipeline system | Multidsciplinary project team |  |  |  | Not yet started
53 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Work with your medical engineers to set up the portable cylinder supply system and manage alarm systems | Multidsciplinary project team |  |  |  | Not yet started
54 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Display posters near the old valves and in key areas to educate staff about the new cylinder setup and the reasons for the switch, reinforcing the new procedures and safety measures | Multidsciplinary project team |  |  |  | Not yet started | 5. Project communication templates
55 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Run the pilot for the agreed length, ensure direct contact between the clinical area and medical engineers throughout the pilot | Multidsciplinary project team |  |  |  | Not yet started
56 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Get feedback from staff about using the portable cylinders and make note of any problems or concerns that come up during the pilot | Project manager |  |  |  | Not yet started
57 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Calculate carbon savings made over the pilot and estimated monetary savings longer term to include in reports and documents making the case for a wider roll-out | Project manager |  |  |  | Not yet started | 7. Measure and calculate emissions and waste tool
58 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Go over the feedback and lessons learned from the pilot to help plan for using cylinders everywhere in the hospital | Project manager |  |  |  | Not yet started
59 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Optional pilot: Put together all the information, feedback, and ideas from the mapping process and the pilot -this includes things like how to communicate, what training is needed, and what to think about when buying cylinders | Project manager |  |  |  | Not yet started
60 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: If not done as part of a pilot, make sure small cylinders are on the pharmacy's stock list and if not, request that your supplier representative adds them to the stock list | Pharmacy |  |  |  | Not yet started
61 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Decide which portable cylinder system should be used for the area | Multidsciplinary project team |  |  |  | Not yet started | 2. Portable cylinder system options and equipment
62 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Make a clear plan for how you'll keep staff and stakeholders informed and involved throughout the process | Project manager |  |  |  | Not yet started | 5. Project communication templates
63 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Assess the number of small cylinders and equipment required based on each area's nitrous oxide usage | Multidsciplinary project team |  |  |  | Not yet started | 6. Approaches to understanding supply and use
64 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Consider any additional accessories or modifications needed for the transition | Pharmacy |  |  |  | Not yet started | 2. Portable cylinder system options and equipment
65 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Provide your gas supplier with approximate numbers of cylinders to be ordered per month and reduce manifold cylinder supply, request for the supplier to stop delivery of manifold cylinders once the transition is complete | Pharmacy |  |  |  | Not yet started | 6. Approaches to understanding supply and use
66 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Place orders for equipment based on the type of portable cylinder system required | Multidsciplinary project team |  |  |  | Not yet started
67 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Make sure the cylinders are stored safely when they arrive | Portering staff |  |  |  | Not yet started
68 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Coordinate with local medical gas portering staff to support the process with the new cylinders, where they will be required and how to supply them to the clinical area, use the portable cylinder system process map in the toolkit to help | Multidsciplinary project team |  |  |  | Not yet started
69 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Train staff how to use the portable cylinders, including safety and troubleshooting, include training on using as much of the cylinder as possible before switching to a new cylinder | Multidsciplinary project team |  |  |  | Not yet started
70 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Let stakeholders know when the switch will happen using the template emails | Project manager |  |  |  | Not yet started | 5. Project communication templates
71 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: When cylinders arrive, have technicians set up the machines to use the small cylinders | Multidsciplinary project team |  |  |  | Not yet started
72 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Securely cap all terminal units in areas switching to a portable cylinder system to prevent accidental use of the medical gas pipeline system | Estates / Facilities |  |  |  | Not yet started
73 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Display posters near the old valves and in key areas to educate staff about the new cylinder setup and the reasons for the switch, reinforcing the new procedures and safety measures | Multidsciplinary project team |  |  |  | Not yet started
74 | 2. Ensure supply of gas is aligned to clinical use | F. Implement supply system alignment: Low clinical use | Transition to a portable cylinder system: Disable system alarms in each clinical area and at the manifolds for areas that have successfully switched to portable cylinder systems | Estates / Facilities |  |  |  | Not yet started
75 | 2. Ensure supply of gas is aligned to clinical use | G. Implement supply system alignment: High clinical use | Optimise supply systems: Decide if the medical gas pipeline system should be replaced with a portable cylinder system, redesigned or optimised -if replaced, follow the actions under 'areas with low clinical use' | Multidsciplinary project team |  |  |  | Not yet started
76 | 2. Ensure supply of gas is aligned to clinical use | G. Implement supply system alignment: High clinical use | Agree waste reduction plan and ensure sign off from relevant staff -use the supporting resources to confirm in writing to clinical leads, the Medical Gas Committee and estates/facilities colleagues | Multidsciplinary project team |  |  |  | Not yet started | 5. Project communication templates
77 | 2. Ensure supply of gas is aligned to clinical use | G. Implement supply system alignment: High clinical use | If agreed to switch to portable cylinder system, follow steps in "Transition to a portable cylinder system" | Multidsciplinary project team |  |  |  | Not yet started
78 | 2. Ensure supply of gas is aligned to clinical use | G. Implement supply system alignment: High clinical use | If agreed to reposition the manifold to sit closer to the clinical areas which it serves, reducing the pipework between them, follow actions in "Improve design of existing systems and evaluate new gas supply needs" | Multidsciplinary project team |  |  |  | Not yet started
79 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Decide whether you can decommission an entire medical gas pipeline system or just a branch of it, once a clinical area does not require it | Multidsciplinary project team |  |  |  | Not yet started
80 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Conduct a risk assessment and develop a detailed decommissioning plan according to Health Technical Memorandum HTM 02-01. Include relevent permits and sign-offs required | Estates / Facilities |  |  |  | Not yet started
81 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Insert terminal unit plugs at all gas outlets connected to the relevant medical gas pipeline system, to signal they are out of service | Estates / Facilities |  |  |  | Not yet started
82 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Deactivate the nitrous oxide or nitrous oxide/oxygen mixture area and plant alarm systems, this may be for the entire medical gas pipeline system or a branch being shut off | Estates / Facilities |  |  |  | Not yet started
83 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Isolate the manifold supply at final distribution system valve for the section/s being shut off and isolate each of the cylinders being removed at the cylinder valve | Estates / Facilities |  |  |  | Not yet started
84 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Replace the area valve service unit (AVSU) nitrous oxide or nitrous oxide/oxygen mixture glass with a NOT IN USE blanking plate | Estates / Facilities |  |  |  | Not yet started
85 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Depressurise the system via the manifold with suitable ventilation to a safe, external location | Estates / Facilities |  |  |  | Not yet started
86 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | For decommissioning a specific section of the pipeline; Shut off the relevant Area Valve Service Unit (AVSU), disable the corresponding alarm system, release pressure from the targeted pipeline segment, seal the downstream AVSU flange with a blank spade, clearly mark the AVSU as out of service and conduct a thorough leak check on the downstream flange using an approved detection solution | Estates / Facilities |  |  |  | Not yet started
87 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Notify all relevant clinical teams and pharmacy services about the decomissioned system | Estates / Facilities |  |  |  | Not yet started
88 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Update the written scheme of the pipeline to reflect the changes | Estates / Facilities |  |  |  | Not yet started
89 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | If the isolation is permanent, consider removing the isolated section of pipeline and sealing off terminal units | Estates / Facilities |  |  |  | Not yet started
90 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Cap any unfinished, partially full cylinders from the now decommissioned manifold | Estates / Facilities |  |  |  | Not yet started
91 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Move any partially full or full cylinders from the decommissioned manifold to other manifolds still in use (rotate stock to ensure it is not sent back to supplier unused), or send back to supplier if no other manifolds | Estates / Facilities |  |  |  | Not yet started
92 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Inform medical gas supplier of discontinued or no longer required cylinder deliveries at each hospital site(s) | Estates / Facilities |  |  |  | Not yet started
93 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Remove all equipment in the manifold room and return it to the supplier | Estates / Facilities |  |  |  | Not yet started
94 | 2. Ensure supply of gas is aligned to clinical use | H. Decommission the medical gas pipeline system | Complete relevent paperwork and communication of completed decomissioning | Estates / Facilities |  |  |  | Not yet started
95 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Ensure optimal delivery schedule is in place to reduce waste -if it is on 'milk-round' deliveries, contact the supplier to change to a demand-driven cylinder management system based on usage data | Pharmacy |  |  |  | Not yet started
96 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Define responsibilities for pharmacy procurement team, portering staff, clinical staff, and suppliers in cylinder management, use the portable cylinder system process map in the toolkit to help | Multidsciplinary project team |  |  |  | Not yet started
97 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Set up a system for portering staff, operating department practitioners, and other relevant staff to report unusual patterns in cylinder delivery or usage, include mechanisms to report increased small cylinder deliveries for portable systems and to report increased large cylinder deliveries for medical gas pipeline systems | Estates / Facilities |  |  |  | Not yet started
98 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Consider implementing electronic tagging systems (e.g RFID), sign-in/out processes, or app-based cylinder management tools | Estates / Facilities |  |  |  | Not yet started
99 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Maintain secure and safe storage areas compliant with health and safety regulations | Multidsciplinary project team |  |  |  | Not yet started
100 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Ensure mandatory training is completed for staff handling gas cylinders and piped systems, including emergency procedures and safety equipment use | Multidsciplinary project team |  |  |  | Not yet started
101 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Ensure that all manifolds have their associated logbooks to support stock control and estimated usage or utilise switchboard data to monitor usage | Estates / Facilities |  |  |  | Not yet started
102 | 3. Continue to optimise systems | I. Enhance stock control of cylinders | Put in place a process to rotate stock to ensure it is not sent back to supplier unused | Estates / Facilities |  |  |  | Not yet started
103 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Schedule and perform annual system pressure tests in accordance with Health Technical Memorandum -02-01, ensure the supply is physically isolated during these tests | Estates / Facilities |  |  |  | Not yet started
104 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Regularly review nitrous oxide data from the Greener NHS Dashboard in medical gas committee or sustainability team meetings, use this data to build understanding of nitrous oxide and nitrous oxide/oxygen mixture usage and improvements at trust level | Medical gas committee |  |  |  | Not yet started | 6. Approaches to understanding supply and use
105 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Identify discrepancies in supply data from the pharmacy procurement team between purchased volumes and expected usage | Multidsciplinary project team |  |  |  | Not yet started | 6. Approaches to understanding supply and use
106 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Create a process for clinical staff and portering staff to report any visible equipment damage | Multidsciplinary project team |  |  |  | Not yet started
107 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Set up regular opportunities for staff to discuss identified inefficiencies and plan corrective actions | Multidsciplinary project team |  |  |  | Not yet started
110 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Check for damage and wear and tear across portable cylinder system parts, replacing equipment when necessary | Multidsciplinary project team |  |  |  | Not yet started
111 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Replace worn parts of the portable cylinder system e.g O rings that may break when yokes are removed (for a modified portable cylinder system on the back of anaesthetic gas machines only) | Multidsciplinary project team |  |  |  | Not yet started
112 | 3. Continue to optimise systems | J. Identify supply system inefficiencies | Replace worn parts of the medical gas pipeline system (terminal units, area valve service units, medical supply units, pressure regulators and valves, pipeline system, alarm and monitors) | Estates / Facilities |  |  |  | Not yet started
113 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | Decide on a leak test (or series of tests) to identify and locate possible leaks and damage at high pressure points, use the toolkit to help identify the best option | Estates / Facilities |  |  |  | Not yet started | 6. Approaches to understanding supply and use
114 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | System wide leak test: Arrange for temporary portable nitrous oxide/oxygen mixture cylinders if needed whilst pipeline supply will be tested | Multidsciplinary project team |  |  |  | Not yet started
115 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | System wide leak test: Tell staff about the test and collect feedback on the approach | Multidsciplinary project team |  |  |  | Not yet started
116 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | System wide leak test: Work with your medical engineers to temporarily disable the medical gas alarm systems | Estates / Facilities |  |  |  | Not yet started
117 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | Schedule the leak test (this should be a system pressure test) | Estates / Facilities |  |  |  | Not yet started
118 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | Conduct the system pressure test and analyse the results | Estates / Facilities |  |  |  | Not yet started
119 | 3. Continue to optimise systems | K. Optimise remaining medical gas pipeline systems | Once a leak is suspected or confirmed through system-wide methods, use a location-specific leak detection method from table 6 to pinpoint the exact location of leaks -while they cannot provide assurance about overall system integrity, they can help to target repairs | Estates / Facilities |  |  |  | Not yet started
120 | 3. Continue to optimise systems | L. Replace damaged or outdated equipment | Embed scheduled replacement into equipment management processes for estates and facilities teams, follow HTM 02-01 guidelines for equipment replacement | Estates / Facilities |  |  |  | Not yet started
121 | 3. Continue to optimise systems | L. Replace damaged or outdated equipment | Establish a system for quick replacement of worn parts and thorough maintenance of damaged or leaking points | Estates / Facilities |  |  |  | Not yet started
122 | 3. Continue to optimise systems | M. Improve design of existing systems and evaluate new gas supply needs | Conduct thorough needs assessments to determine clinical necessity for piped nitrous oxide supply systems and consider portable cylinder systems or manifold repositioning before installing new piped systems | Medical gas committee |  |  |  | Not yet started
123 | 3. Continue to optimise systems | M. Improve design of existing systems and evaluate new gas supply needs | Ensure manifold spaces are appropriately sized and located based on clinical requirement, avoid oversized manifold spaces with excess connections and cylinders and design manifolds with shorter pipe distances to points of care | Medical gas committee |  |  |  | Not yet started
124 | 3. Continue to optimise systems | M. Improve design of existing systems and evaluate new gas supply needs | Assess the efficiency and necessity of existing piped supply systems | Medical gas committee |  |  |  | Not yet started
125 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Train staff to turn off and disconnect equipment when not in use | Clinician |  |  |  | Not yet started
126 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Establish a system for regular equipment checks and prompt repair/replacement | Clinician |  |  |  | Not yet started
127 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Develop checklists or protocols for setting up and shutting down equipment and incorporate equipment checks into post-procedure routines e.g O rings that may break when yokes are removed | Clinician |  |  |  | Not yet started
128 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Train staff on proper cylinder use and full depletion before switching, ensure backup cylinders are readily available | Clinician |  |  |  | Not yet started
129 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Train staff where relevent to disconnect demand valves from the gas supply when not in use | Clinician |  |  |  | Not yet started
130 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Run a communications campaign where relevent to ensure demand valves are removed from terminal wall outlets when not needed -use the posters for clinical best practice in the Internal messaging pack as reminders | Clinician |  |  |  | Not yet started
132 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Conduct regular audits and maintenance processes to check for damage and wear across portable cylinder system parts and replace them | Clinician |  |  |  | Not yet started
133 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Place posters, signs, or labels near nitrous oxide equipment as reminders | Clinician |  |  |  | Not yet started | 5. Project communication templates
134 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Share advice and materials with clinicians on using the lowest effective dose and minimising duration of use | Clinician |  |  |  | Not yet started
135 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Assign team members to manage nitrous oxide equipment and support best practices | Clinician |  |  |  | Not yet started
136 | 3. Continue to optimise systems | N. Reduce waste through clinical practice | Ensure a process by which a clinical staff member checks small cylinders on portable systems have been switched off after use | Clinician |  |  |  | Not yet started
137 | 3. Continue to optimise systems | O. Catalytic destruction technology | Focus on aligning supply systems to clinical need and ongoing optimisation before considering catalytic destruction technology | Multidsciplinary project team |  |  |  | Not yet started
138 | 3. Continue to optimise systems | O. Catalytic destruction technology | If considering catalytic destruction units, carefully evaluate costs, practicality, and potential benefits within the specific clinical context | Multidsciplinary project team |  |  |  | Not yet started
Step one:
To use this tool accurately, select the stage of work you are doing at the moment.
Step two:
Then, select what you need to do at this stage, if you are unsure do not filter this and you will see all the actions in order.
Step three:
Add an optional filter to see the actions only for you, or others.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Key
Key
Not yet started
Planning
In progress
Pending/awaiting action
Complete
Ongoing task
Supporting tool or guidance
1. Nitrous oxide and nitrous oxide/oxygen mixture use and supply in the NHS
2. Portable cylinder system options and equipment
3. Project management templates
4. Key actions checklist
5. Project communication templates
6. Approaches to understanding supply and use
7. Measure and calculate emissions and waste tool
8. Supply system map and decision template
9. Developing a business case